## Sheet1
MODERATOR: | Rohit |  | Relative sizing established: | A, 3, 5, 8 and K
A effort, complexity and uncertainty is very LOW
Estimator | Yamini |  |  | K effort, complexity and uncertainty is very HIGH
Arun
User Story | Round 1 |  | Discussion Notes | Round 2 |  | Discussion Notes | Final Decision
| Arun | Yamini |  | Arun | Yamini
As a Data Analyst, I want to practice and implement my skills through a real-world project, so I can apply theoretical knowledge to practical scenarios, gain hands-on experience, and enhance my ability to derive actionable insights from data. (T1USJR-15) | 8 | 5 | As per Yamini's view as the data analyst is already in the same field it will be easier for him to implement the skills in the real-world project. According to Arun, Data Analysis require too much mathematical background, and it also comes with a lot of complex modeling, so it will be a complex task to complete. | 8 | 8 | Accoding to the discussion we had, Data Analyst could be a entry level person and the task at hand might be complex for him. | 8
As a Mobile App Developer, I want to revise my resume according to the prioritized feedback so that it accurately reflects my skills and experiences, improves my chances of landing job opportunities, and showcases my expertise in mobile app development. (T1USJR-49) | 8 | 8 | As per Yamini’s view it is a complex task. Revising a resume based on prioritized feedback involves not only editing content but also analyzing and incorporating feedback effectively. The developer needs to ensure that their skills and experiences are accurately and effectively presented, which requires a good understanding of how to highlight key competencies and achievements. According to Arun, tailoring the resume to showcase expertise in mobile app development can involve strategic changes to structure, wording, and the inclusion of relevant projects or technologies. Overall, it requires careful consideration and execution to enhance the resume's impact. | 8 | 8 | Since both estimators agree to same vote, we conclude with the complexity. | 8
As a Chef, I want to choose a clean and professional design and organize content for easy navigation in my portfolio, so I can effectively showcase my culinary creations, recipes, and kitchen skills to potential employers and clients. (T1USJR-25) | 3 | 3 | As Yamini suggested, This user story is easy. Choosing a clean, professional design and organizing content for easy navigation involves basic design principles and straightforward content arrangement to showcase the chef's culinary creations, recipes, and kitchen skills effectively. As per Arun, this is also a easy task, since the chef has to select the clean and professional design should be a visual and easy task for a Chef. | K | K | As we discussed it again, since he/she is a chef, he/she does not have enough technical expertise in this area. He/she might need to get some help from others to complete this task. Some tasks look easy but the expertise is required to complete those tasks. | K
As a Digital Content Creator, I want to gather feedback from peers on my content portfolio so that I can improve the quality, engagement, and effectiveness of my digital content. (T1USJR-36) | 3 | 5 | This user story is moderate Gathering feedback from peers on the content portfolio involves straightforward tasks such as soliciting opinions, reviewing suggestions, and making improvements to enhance the quality, engagement, and effectiveness of the digital content. According to Arun, since he is already a Digital Content Creator, it will be an easy task for him. | 3 | 5 | Even though it looks like a simple task for him. But there could be unexpected curve balls he might face. | 5
As a Technical Support Specialist, I need to share my updated portfolio with reviewers to get further feedback and make improvements to better reflect my support capabilities. (T1USJR-52) | 3 | 3 | This user story is easy. Sharing an updated portfolio with reviewers to gather feedback involves simple tasks such as distributing the portfolio, collecting feedback, and making improvements to better reflect support capabilities. | 3 | 3 | Both estimators still agree on the decision as sending the portfolio for the peer review to suggest improvements is reletively easy task and require less expertise to share the portfolio than building it. | 3
User Story | Priority | Ranking
As a Software Developer, I want to complete relevant coursework and training programs, so I can improve my coding skills and stay updated with the latest technologies and best practices, ensuring I deliver high-quality software solutions. (T1USJR-14) | High | 8
As an Operations Manager, I need to evaluate the progress of our operational processes to identify any bottlenecks and ensure smooth and efficient workflow. (T1USJR-16) | High | 8
As a Quality Assurance Tester, I need to complete the testing project for the new software release to ensure it meets the quality standards and is ready for deployment. (T1USJR-17) | Medium | 5
As a Network Engineer, I need to research industry standards to ensure our network infrastructure is up-to-date and complies with the latest security protocols. (T1USJR-18) | High | K
As a Healthcare Administrator, I need to draft my initial resume to accurately reflect my skills and experiences when applying for a higher administrative position. (T1USJR-19) | High | 8
As a Product Manager, I need to incorporate newly acquired skills in my resume to highlight my professional growth and readiness for advanced responsibilities. (T1USJR-20) | High | 8
As a Business Analyst, I want to seek feedback from mentors or peers and make necessary revisions and improvements, so I can ensure my analysis and reports are accurate, comprehensive, and aligned with business objectives. (T1USJR-21) | Medium | 5
As an SEO Specialist, I want to finalize my resume by proofreading for errors and saving it in multiple formats so that it is polished and ready to be submitted to potential employers on different platforms. (T1USJR-22) | Low | 3
As a Graphic Designer, I want to decide on the format (website, PDF, etc.) and outline sections and content for my portfolio, so I can effectively showcase my design skills, creativity, and completed projects to potential clients and employers. (T1USJR-23) | Medium | 5
As a UX/UI Designer, I want to write project descriptions and include visuals, prototypes, and links to live projects in my portfolio, so I can effectively demonstrate my design process, user-centered approach, and the impact of my work to potential employers and clients. (T1USJR-24) | Medium | 5
As a Technical Writer, I want to seek feedback from peers or mentors and make revisions and updates to my documents so that the content is accurate, clear, and effectively communicates technical information to the target audience. (T1USJR-26) | Low | 3
As a Supply Chain Analyst, I need to publish my portfolio to showcase my analytical skills and successful projects to potential employers or clients. (T1USJR-27) | High | 8
As a Project Manager, I want to identify peer reviewers, share my resume with context and specify areas for feedback, and collect input and suggestions from peers, so I can refine my resume to better highlight my project management skills and achievements. (T1USJR-34) | High | 8
As a Financial Analyst, I want to collect all feedback received on my resume, categorize feedback into different types (e.g., content, format, clarity), and prioritize changes based on the importance and impact on the resume, so I can ensure my resume effectively highlights my analytical skills and financial expertise. (T1USJR-35) | High | 8
As a Machine Learning Engineer, I want to analyze feedback received on my machine learning projects and prioritize changes so that I can improve the performance, accuracy, and usability of my models and solutions. (T1USJR-37) | High | K
As a Cloud Engineer, I want to share my revised resume with reviewers to gather additional feedback so that I can ensure it accurately represents my skills and experiences, making it more effective in securing job opportunities. (T1USJR-50) | High | K
As a Database Administrator, I need to revise my professional portfolio based on feedback from my peers to ensure it accurately showcases my competencies and achievements. (T1USJR-51) | High | 8
As a Human Resource Specialist, I want to be able to research and identify relevant learning resources for employee development, so I can provide accurate and effective training recommendations, ensuring our team acquires the necessary skills for their roles efficiently. (T1USJR-6) | Medium | 5
As a Digital Marketer, I want to create a detailed learning plan, so I can systematically enhance my skills in the latest digital marketing trends and tools, ensuring I stay ahead in the industry and drive better results for my campaigns. (T1USJR-7) | Medium | 5
As a Customer Success Manager, I want to complete relevant coursework and training so that I can enhance my skills and knowledge, effectively support my customers, and drive their success.Follow through with the learning plan. (T1USJR-8) | Low | 3
As an E-Commerce Manager, I want to practice and implement my learning through hands-on projects and active participation in relevant online communities so that I can apply theoretical knowledge in real-world scenarios and enhance my practical skills. (T1USJR-9) | Medium | 5
As a Content Writer, I need to evaluate the progress of my content development to ensure that the articles meet the editorial standards and deadlines are adhered to. (T1USJR-10) | Low | 3
As a Sales Manager, I need to complete the sales strategy project on time to ensure that our quarterly sales targets are met and the team has a clear direction for their efforts. (T1USJR-11) | High | 8
As an IT Consultant, I want to research and identify relevant learning resources so that I can stay up-to-date with the latest technologies, methodologies, and best practices in the IT industry. (T1USJR-12) | High | K
As a System Analyst, I want to create a comprehensive learning plan so that I can systematically acquire the necessary skills and knowledge to excel in my role and contribute effectively to system analysis and improvement projects. (T1USJR-13) | High | 8